MainLine

Project Management Software

By

Minuteman Systems

P.O. Box 152

Belmont MA  02178

Preface

Copyright Information

Copyright 1992, by Minuteman Systems

The software and the disks on which it is contained are licensed

to you, for your own use. This is copyrighted software. You are

not obtaining title to the software or any copyright rights.

You may not sublicense, rent, lease, convey, modify, trans-

late, convert to any other programming language, decompile, or

disassemble the software for any purpose.

You may make as many copies of this software as you need for

backup purposes. You may use this software on more than one

computer, provided there is no chance it will be used simultane-

ously on more than one computer.

Preface  v

Registration Information

This program is supplied as Shareware. This means that you

may evaluate the program for free, but are required to pay a

registration fee if you keep it and use it.

Note that any fee paid to a Shareware distribution company or

similar supplier does not replace, nor contribute towards, the

registration fee.

If you are satisfied with the program and wish to use it, you

may register it by filling out a hardcopy of the included file

ORDER.TXT. Send it with a check or money order for $29.95 to

Minuteman Systems, PO Box 152, Belmont, Massachusetts, 02178.

As a registered user, you will receive

o  A printed, bound User's Manual.

o  Free updates for one year.

o  Telephone service.

o  A personalized diskette with your name and a serial number.

Also, the registration screen usually presented when exiting

the program will be disabled.

Incentive Plan - Once you have registered, have acquaintences

list your name as a reference when they register. You will receive

a $5.00 rebate.

vi  Preface

Notice

This software is supplied as-is. There are no warranties, ex-

pressed or implied.

Minuteman Systems disclaims all warranties relating to this

software, whether expressed or implied, including but not lim-

ited to any implied warranties of merchantability and fitness

for a particular purpose, and all such warranties are expressly

and specifically disclaimed. Neither Minuteman Systems nor any-

one else who has been involved in the creation, production,

or delivery of this software shall be liable for any indirect,

consequential, or incidental damages arising out of the use

or inability to use such software even if Minuteman Systems

has been advised of the possibility of such damages or claims.

In no event shall Minuteman Systems' liability for any damage

ever exceed the price paid for the license to use the software,

regardless of the form of claim. The person using the soft-

ware bears all risk as to the quality and performance of the

software.

Some states do not allow the exclusion of the limit of liability

for consequential or incidental damages, so the above limitation

may not apply to you.

This agreement shall be governed by the laws of the Commonwealth

of Massachusetts and shall inure to the benefit of Minuteman

Systems and any successors, administrators, heirs and assigns.

Any action or proceeding brought by either party against the

other shall be brought only in a STATE or FEDERAL COURT of com-

petent jurisdiction located in Middlesex County, Massachusetts.

The parties hereby consent to in personam jurisdiction of said

courts.

Preface  vii

CONTENTS

Preface...............................................     v

1 Introduction.........................................     1

1.1 How This Manual Is Organized......................     1

2 Installation.........................................     2

2.1 System Considerations.............................     2

2.2 Installation Procedure............................     4

3 Trial Run - 1st Pass.................................     6

3.1 The Initial Screen................................     6

3.2 Moving Around - Key Commands......................     8

3.3 The Menu-Command Line.............................    10

3.4 Adding a Task.....................................    11

3.5 Storing a Project.................................    14

3.6 Printing Reports..................................    14

3.7 Exiting...........................................    14

3.8 Examining The Reports.............................    15

4 Trial Run - 2nd Pass.................................    18

4.1 Reading In A Project..............................    18

4.2 Editing an Existing Task..........................    19

4.3 Inserting, Deleting, Moving Lines.................    20

4.4 Deleting A Task...................................    24

4.5 Adding Descriptions to Groups of Tasks............    26

4.6 Adding A Date and Labels to The Display...........    26

4.7 Locating Tasks - The "Search" Function............    29

4.8 The Wait Function.................................    29

4.9 Changing Program Configuration....................    31

5 Advanced Topics......................................    35

5.1 System Capabilities...............................    35

5.2 Following The Critical Path.......................    35

iii

5.3 The Journal File - Recovering Damaged Project

Files.............................................    35

5.4 Attaching Fixed Dates to Milestones...............    36

5.5 Project Rollups...................................    36

5.6 Renumbering Tasks and Milestones..................    39

5.7 Copying A Group of Projects.......................    39

5.8 Importing Projects................................    41

6 Command Listing......................................    43

6.1 Filing............................................    43

6.2 Global............................................    43

6.3 Exit..............................................    44

6.4 Tasks.............................................    44

6.5 Display...........................................    44

6.6 Print.............................................    45

Appendix A  QUICK-START INFORMATION.......................    47

A.1 Starting Up........................................    47

A.2 Moving Around The Screen...........................    47

A.3 Calling Up Commands................................    49

A.4 Basics of Editing and Generating Reports...........    49

A.5 Notes on Dates and Calculations....................    50

Appendix B  SELECTING OUTPUT FORMATS......................    51

Appendix C  SERVICE.......................................    53

iv

FIGURES

1     Blank Project.....................................     7

2     1 Task Added......................................    13

3     DEMO.DAT..........................................    16

4     DEMO.RPT..........................................    17

5     Tasks Added.......................................    22

6     Moved Lines.......................................    23

7     Adding Comments...................................    27

8     Date and Label Fields.............................    28

9     Using The Task Wait Function......................    30

10    Global Configuration Menu.........................    32

11    Using Rollup Tasks................................    38

v

1  Introduction

The principal job of the MainLine Project Management Program is

to develop a schedule in a clear and understandable format, for

the purposes of

1. Identifying the parts of the project and their interdependen-

cies.

2. Allowing easy changes to the schedule for "what if" purposes.

3. Providing compact reports suitable for presentations, and

compatible with electronic mail systems for distribution to

those working on the project.

1.1  How This Manual Is Organized

Section 2 describes the method for installing the program on the

machine. It also discusses the requirements of the computer this

program is to run on.

Section 3 and Section 4 illustrate how to use MainLine by means

of a series of examples.

Section 3 goes over the basics - turning on the program, creat-

ing a simple project, and generating some reports.

Section 4 demonstrates with further examples how to edit a

project and manipulate the display of a project on the screen.

Section 5 describes some advanced features.

Section 6 lists all the individual commands available and de-

scribes each briefly.

Appendix A includes "quick-start" information if you wish to get

up-and-running prior to having read this whole manual.

Appendix B gives further information on formatting the schedule

output for printing and electronic mailing.

1

2  Installation

To install and use this program, all that is required is famil-

iarity with the basics of DOS operation. If you aren't experi-

enced with creating directories and copying files, consult the

DOS documentation with your system.

2.1  System Considerations

This program is intended to be run on IBM-style personal com-

puters and exact compatibles. The program has been successfully

tested and used on numerous machines.

Speed of the program will vary depending on the model of PC

used. The program was developed and tested on 20MHz 386-SX

machines and found to have very usable speed. It has been tested

on older machines including 8 MHz "XT" machines - while the

performance is slower, it is still quite usable.

Whatver machine used should have at least 360K of RAM memory

free and available.

Note - The presence on a system of Terminate-And-Stay-Resident

programs (TSRs), memory managers, or Local Area Network (LAN)

software may interfere with the operation of this program. "In-

terference" usually means that the program cannot load and ex-

ecute. However, in borderline cases there may be misoperations

during the running of the program. This includes things like

running out of memory, or disturbances of the display. If you

are experiencing difficulty loading or running this program, and

any of those other types of software are installed on your sys-

tem, try removing them or disabling them in various combinations

to determine what is causing the problem.

2

Video Considerations - The first time the program is used, it

will default to run in a black and white mode compatible with

most if not all video cards and display monitors available. The

program's command menu has options for selecting the colors

displayed, and for changing the resolution of the display.

(See Section 4.9.) These selections may then be stored away

as defaults for future use.

3

2.2  Installation Procedure

Registered users receive a diskette containing the updated,

executable code and related files in non-compressed format. They

should be copied directly into the working subdirectory.

Diskettes obtained from Shareware vendors include the following

files;

o  MAINLINE.EXE - A compressed, self-extracting file containing

the executable code, this documentation, and several data

files.

o  INSTALL.BAT - Installation Batch File

o  INSTALL.TXT - Instructions for using INSTALL.BAT to install

the program.

o  ORDER.TXT - A Form for registering the program

o  README.1ST - A brief description of the program, including

installation considerations.

o  PACKING.LST - A list of the included files.

Diskette vendors may also place other files on the diskette.

Before doing any installation, it is best to make a backup copy

of the supplied diskette. This is easily done by copying all

files on the diskette using the DOS command;

DISKCOPY b: b: (Assuming diskette drive is "b" - otherwise

substitute the proper disk drive letter.)

To install the program, run the installation batch file. First

set your default drive to the diskette drive.

Then type INSTALL from: to: followed by ENTER, substituting the

diskette drive and the harddisk drive respectively. I.E. A:, B:,

C:, D:. Be sure to include the colons.

A subdirectory MAINLINE will be created. The following files

will be installed in it;

4

o  MAINLINE.DOC - This file, the User's Manual.

o  ML.EXE - The executable program file.

o  SMCGA.FNT - Fonts used in high resolution black/white dis-

play.

o  SMVGA.FNT - Fonts used in high resolution color display.

If for some reason the installation procedure does not work,

install the program manually as follows;

Create a subdirectory on your harddisk where you will do your

project work. Example - C:\MAINLINE. Copy MAINLINE.EXE into this

subdirectory. Set your default drive/directory to C:\MAINLINE.

Extract the file by typing MAINLINE (followed by ENTER).

If you obtained the program from a bulletin board or an on-line

service such as COMPUSERVE, all the above files are bundled into

MAINLINE.EXE. Use the manual installation procedure described

above.

5

3  Trial Run - 1st Pass

This section will go through the real basics - turning the

program on, creating and saving a simple project, generating

some reports, and exiting the program.

First set the default drive to the one where you have stored

the program. Start the program by entering ML followed by

ENTER or Carriage Return (CR).

3.1  The Initial Screen

See Figure 1. After a few seconds the display will show a

Gantt/Pert chart for a minimal project. It will have only a

start milestone, a single task, and an end milestone.

Here are some important things to note about the way a schedule

is displayed.

o  The Calendar - Dates run left to right across the top of

the display. Month, date, and day-of-week (MTWTF) are shown.

Only week-workdays are used, and there are no provisions for

holidays.

o  Milestones - Each Milestone is represented by an asterisk (*)

and is shown as occurring on one day only.

o  Tasks - Tasks are represented as equal signs (=) if they are

on the critical path, or dash-lines (-) if they aren't.

o  ID's - Each task or milestone must have a unique identifying

number which is displayed below it ("10" for the "Start"

Milestone).

o  Line Numbers - Each task or milestone is represented on a

3-row "Line". ("1" for the Start milestone, "2" for "Task".)

You can assign the Line Number for any Task or Milestone, to

format the Schedule the way you want.

That's enough description for now - more characteristics will be

described as we use them.

6

Figure 1: Blank Project

Press "/" or "\" For Command Menu       MainLine Rev 1.4

.----------------------+---------------------+------------------.

|_____Mar '92__________|___ Apr '92 _________|___ May '92 ______|

|    0    1    2    2  | 0    1    1    2    |    0    1    2   |

|    6    3    0    7  | 3    0    7    4    |    8    5    2   |

Date:16-Mar-92 |MTWTFMTWTFMTWTFMTWTFMT|TFMTWTFMTWTFMTWTFMTWT|MTWTFMTWTFMTWTFMTW|

.--------------+----+----+----+----+----+----+----+----+----+----+----+----+---|

|Blank       1 |Start    .    .    .    .    .    .    .    .    .    .    .   |

|              |*   .    .    .    .    .    .    .    .    .    .    .    .   |

|              | 10 .    .    .    .    .    .    .    .    .    .    .    .   |

|            2 | Task    .    .    .    .    .    .    .    .    .    .    .   |

|              | ===================^   .    .    .    .    .    .    .    .   |

|              |  20.    .    .    .    .    .    .    .    .    .    .    .   |

|            3 |    .    .    .    .End .    .    .    .    .    .    .    .   |

|              |    .    .    .    .*   .    .    .    .    .    .    .    .   |

|              |    .    .    .    . 30 .    .    .    .    .    .    .    .   |

|            4 |    .    .    .    .    .    .    .    .    .    .    .    .   |

|              |    .    .    .    .    .    .    .    .    .    .    .    .   |

|              |    .    .    .    .    .    .    .    .    .    .    .    .   |

|            5 |    .    .    .    .    .    .    .    .    .    .    .    .   |

|              |    .    .    .    .    .    .    .    .    .    .    .    .   |

|              |    .    .    .    .    .    .    .    .    .    .    .    .   |

|            6 |    .    .    .    .    .    .    .    .    .    .    .    .   |

|              |    .    .    .    .    .    .    .    .    .    .    .    .   |

|              |    .    .    .    .    .    .    .    .    .    .    .    .   |

`--------------+----+----+----+----+----+----+----+----+----+----+----+----+---|

|MTWTFMTWTFMTWTFMTWTFMT|TFMTWTFMTWTFMTWTFMTWT|MTWTFMTWTFMTWTFMTW|

|    0    1    2    2  | 0    1    1    2    |    0    1    2   |

|    6    3    0    7  | 3    0    7    4    |    8    5    2   |

|     Mar '92          |    Apr '92          |    May '92       |

`----------------------+---------------------+------------------'

7

3.2  Moving Around - Key Commands

You can use keyboard keys to move around and look at other parts

of the schedule.

You can use the UP(^) and DOWN(v) arrows to scan through the

schedule one line at a time.

The "PAGE UP" and "PAGE DOWN" keys will move the display one

screen at a time.

Pressing the RIGHT and LEFT Arrow keys moves the display hori-

zontally.

Note - If multiple Arrow or PAGE UP/DOWN keys are entered

quickly, after a brief pause the screen will be updated only

once. This is a great timesaver. It reduces the time spent

waiting for the screen to be redrawn. To demonstrate this fea-

ture, press RightArrow three times quickly. This only works with

multiple entries of the same key type.

These and other key selections are listed below;

________________________________________________________________

Key___________Function__________________________________________

Down Arrow    Advance Screen One Line

Up Arrow      Back Screen One Line

Right         Move Forwards in time.

Arrow

Left Arrow    Move Backwards in Time

PAGE DOWN     Advance to Next Screen

PAGE UP       Go Back 1 Screen

8

________________________________________________________________

Key___________Function__________________________________________

HOME          Move to Top-most Screen and Start of Calendar

CTRL-T        Move to Top-most Screen

CTRL-B        Move To Bottom-most Screen

CTRL-L        Move Horizontally Left To Start of Calendar

CTRL-R        Move Horizontally Right to Latest Used Date

CTRL-F        Find Task/Milestone

+             Follow the critical path forwards in time

-             Follow the critical path backwards in time

"|"           Go To A Specific Line Number

"\"_or_"/"____Activate_Menu-Command_Line________________________

9

3.3  The Menu-Command Line

There are many commands for editing, filing, generating outputs,

etc. The majority are activated by use of a Menu-Command Line.

The Menu-Command line is called up by pressing the "\" or "/"

key. (Press "/" Now)

Note that the commands "Filing,Global,Exit,Tasks,Display,Print"

are displayed at the top of the screen, and that "Filing" is

highlighted.

The Highlight may be moved around by pressing the right- or

left- arrows. Try it, but then return to "Filing".

Pressing ENTER (don't do it yet!) executes whichever command

is highlighted. This may result in the immediate execution of a

command, or the appearance of a nested Command line.

With "Filing" still highlighted, hit ENTER now and note that the

command line "Get, Store, New, Import" appears.

Note - You may also activate a command directly by pressing the

key of the first letter of the command. It is not necessary to

press ENTER when so doing.

While viewing the Menu-Command Line, screen movement keys no

longer operate. Pressing BACKSPACE or ESCAPE at any time backs

up one level in the Menu-Command line. Pressing BACKSPACE or

ESCAPE when at the top level exits the Menu-Command Line and

normal screen viewing ability returns. (Hit BACKSPACE now.)

From here on, sequences of using the command line will be de-

scribed as follows;

"\+Filing+Store" means execute the series of menu choices start-

ing with "\" or "/", then "Filing", "Store".

10

3.4  Adding a Task

Execute the following command line; \+Tasks+Add_Task

You will be prompted for a task number - enter "25". (All en-

tries require termination by ENTER.)

Enter "t" or ENTER when prompted to select a Task or Milestone.

You will be asked to specify the ID of a Task or Milestone which

the new task is to succeed - enter "20".

You will be asked to specify the ID of a Task or Milestone which

the new task is to preceed - enter "30". (You don't have to

enter anything here, you could leave it blank - we'll just

include it for this exercise.)

A Task Data Sheet for task 25 will now appear at the bottom

of the screen. You may edit any of the task's data entries by

selecting a letter/number associated with the data, pressing

ENTER, and then entering the data.

Enter "c" (with ENTER) to edit the Title. Then enter "New

Task".

"New Task" should appear in the Title field of the Task Data

Sheet.

Enter "d" to edit the Duration. Then enter "20" for 20 working

days.

To leave the editing mode, enter "x" for Exit.

The full screen is displayed again. It should look like Fig-

ure 2.

Note the following about the new task;

o  It is chronologically between the "Task" and the "End".

11

o  It is on line 2.

o  It is on the critical path.

Note 1 - Note that the screen-movement keys (Arrows, PG UP/DN,

etc, all function while the task editor is working.)

Note 2 - A default line number is always supplied, typically

the same line number as that of the "After Task?" entry. When

the Task Editor is active, you may change the line number as

follows;

Enter "l" to select which line the task should appear on. Use

BACKSPACE to erase the present line number, then enter the new

line number.

Note 3 - Notice that the top line of the display has changed.

When the program was first activated, the top line contained a

message indicating how to activate the command menu. After the

first time that the command menu is used, the top line message

is replaced with information describing the name of the present

project, and the percentage of MainLine's project-handling

capability that is being used. Since MainLine can handle up

to 150 tasks and/or milestones, the percentage shown now is

quite small.

12

Figure 2: 1 Task Added

Project=<DEMO>      Usage = 2%             MainLine Rev 1.4

.----------------------+---------------------+------------------.

|_____Mar '92__________|___ Apr '92 _________|___ May '92 ______|

|    0    1    2    2  | 0    1    1    2    |    0    1    2   |

|    6    3    0    7  | 3    0    7    4    |    8    5    2   |

Date:16-Mar-92 |MTWTFMTWTFMTWTFMTWTFMT|TFMTWTFMTWTFMTWTFMTWT|MTWTFMTWTFMTWTFMTW|

.--------------+----+----+----+----+----+----+----+----+----+----+----+----+---|

|Blank       1 |Start    .    .    .    .    .    .    .    .    .    .    .   |

|              |*   .    .    .    .    .    .    .    .    .    .    .    .   |

|              | 10 .    .    .    .    .    .    .    .    .    .    .    .   |

|            2 | Task    .    .    . New Task.    .    .    .    .    .    .   |

|              | ===================^===================^   .    .    .    .   |

|              |  20.    .    .    .  25.    .    .    .    .    .    .    .   |

|            3 |    .    .    .    .    .    .    .    .End .    .    .    .   |

|              |    .    .    .    .    .    .    .    .*   .    .    .    .   |

|              |    .    .    .    .    .    .    .    . 30 .    .    .    .   |

|            4 |    .    .    .    .    .    .    .    .    .    .    .    .   |

|              |    .    .    .    .    .    .    .    .    .    .    .    .   |

|              |    .    .    .    .    .    .    .    .    .    .    .    .   |

|            5 |    .    .    .    .    .    .    .    .    .    .    .    .   |

|              |    .    .    .    .    .    .    .    .    .    .    .    .   |

|              |    .    .    .    .    .    .    .    .    .    .    .    .   |

|            6 |    .    .    .    .    .    .    .    .    .    .    .    .   |

|              |    .    .    .    .    .    .    .    .    .    .    .    .   |

|              |    .    .    .    .    .    .    .    .    .    .    .    .   |

`--------------+----+----+----+----+----+----+----+----+----+----+----+----+---|

|MTWTFMTWTFMTWTFMTWTFMT|TFMTWTFMTWTFMTWTFMTWT|MTWTFMTWTFMTWTFMTW|

|    0    1    2    2  | 0    1    1    2    |    0    1    2   |

|    6    3    0    7  | 3    0    7    4    |    8    5    2   |

|     Mar '92          |    Apr '92          |    May '92       |

`----------------------+---------------------+------------------'

13

3.5  Storing a Project

In order to store the edited project under a new name, do the

following;

Execute /+Filing+Store

You will be prompted for the name to store it under - a default

of "mlwork" is shown in brackets.

Type "demo" for the name and press ENTER.

The data base for this project has now been saved. The project

could be edited further (remember to store again after addi-

tional changes), or you could exit, restart the program, and

load the stored project.

3.6  Printing Reports

Before exiting let's generate some output reports. We'll just

create the reports now, and examine them after exiting.

Create a schedule report by executing \+Print+Partial_Schedule.

Create a date report by executing \+Print+Date.

Create a task-milestone report by executing \+Print+Task_Detail

3.7  Exiting

Let's temporarily exit.

Enter the commands \+Exit

14

3.8  Examining The Reports

You should be back to the DOS prompt.

Enter the command

C:\MAINLINE>DIR

You will get a directory listing which should include the fol-

lowing files

1. ML.EXE - The executable MainLine file

2. DEMO.PRJ - The data file for the demo project you have cre-

ated.

3. DEMO.TXT - The Schedule for DEMO

4. DEMO.DAT - A Date Report for DEMO

5. DEMO.RPT - A complete report with all the data of all the

tasks and milestones in DEMO.

6. MLJRNL.PRJ - A backup file to protect project data. (See

Section 5.3.)

DEMO.TXT is a text file containing the schedule. It will be

132 columns wide. It should look almost exactly like Figure 2.

(Figure 2 has been modified here to be 80 columns wide to fit

better in this manual.)

You can examine DEMO.TXT with the TYPE command or with a text

editor. You can mail it to anyone on your network. You can send

it to any ASCII printer. If you print it out in LANDSCAPE on

a laser printer, a viewgraph/transparency can be made which is

suitable for use in presentations.

DEMO.DAT lists the start- and end- dates for all the tasks and

milestones in DEMO. It is reproduced in Figure 3

DEMO.RPT lists all tasks and milestones in DEMO, with their

complete data - predecessors, titles, start and end dates, etc.

It is listed in Figure 4

15

Note - Any change to a .PRJ file file could make the file un-

usable. Never try to directly edit or otherwise change a .PRJ

file. Don't even try to view it with a word processor or text

editor.

Figure 3: DEMO.DAT

Report Date: 16-Mar-92

Task and Milestone Date Report        Project Name: demo

--------------------

Task# Typ Description                               Start      End

----- --- ----------------------------------------  ---------  ---------

10   S   Blank               Start                 02-Mar-92  02-Mar-92

20   T                       Task                  03-Mar-92  30-Mar-92

25   t                       New Task              31-Mar-92  27-Apr-92

30   F                       End                   27-Apr-92  27-Apr-92

16

Figure 4: DEMO.RPT

Report Date: 16-Mar-92

Task and Milestone Detail Report      Project Name: demo

--------------------

*******************************************************************************

Task #  10     Type S    Description; Blank                 Start

Start:02-Mar-92  End:02-Mar-92  Duration:  0      Wait :  0

Display Line:  1

Predecessors ;

-------------------------------------------------------------------------------

Task #  20     Type T    Description;                       Task

Start:03-Mar-92  End:30-Mar-92  Duration:  20     Wait :  0

Display Line:  2

Predecessors ;  10,

-------------------------------------------------------------------------------

Task #  30     Type F    Description;                       End

Start:27-Apr-92  End:27-Apr-92  Duration:  0      Wait :  0

Display Line:  3

Predecessors ;  25,

-------------------------------------------------------------------------------

Task #  25     Type t    Description;                       New Task

Start:31-Mar-92  End:27-Apr-92  Duration:  20     Wait :  0

Display Line:  2

Predecessors ;  20,

-------------------------------------------------------------------------------

17

4  Trial Run - 2nd Pass

In the previous chapter we demonstrated the very basics; turning

the program on, creating and storing a simple project, generat-

ing some reports, and exiting.

This chapter will demonstrate in more detail the functions of

MainLine.

We'll start by reading back in the project that was previously

created.

4.1  Reading In A Project

Enter ML to start the program. Execute the command se-

quence \+Filing+Get.

Select project demo. You may do this either of two ways. Press-

ing ENTER will load the highlighted project. (Arrow keys and

PAGE UP/DOWN keys move the highlight around the displayed list

of existing project files.) Or, just type in the project name

DEMO followed by ENTER.

Note - Another way to load a project is to include the

name of the project when starting Mainline. I.E. entering ML

DEMO at the DOS prompt would have automatically loaded the

DEMO project.

18

4.2  Editing an Existing Task

Before demonstrating more functions, lets first update the

project to represent something a little more specific.

Call up the Task Editor for Task 20 by entering the command

\+Tasks+Edit

When prompted for a task number, enter 20.

Select the Title by entering "c". Erase the present title using

the BACKSPACE key, and enter the new title "Define".

In a similar manner, edit the task duration (field "d") to be 10

days.

Select task 25 for editing by entering "n" (for New task) and

the Task Data Sheet for Task 25 will appear. Using the procedure

above, change its title to "Develop".

Select "x" to end the editing session.

This has demonstrated how to make changes to an existing set of

tasks or milestones.

Note that in editing entries the cursor may be positioned using

the right- and left-arrows, and new characters may be inserted

by typing.

19

4.3  Inserting, Deleting, Moving Lines

The lines on the screen may be changed much like those in a

spreadsheet. Blank lines may be added or deleted, or blocks of

lines may be moved around.

To insert some blank lines execute \+Display+Add_lines.

When prompted, enter that you want to add lines before line 3,

and that you want to add 3 lines. Note on the screen that the

END task has been "pushed down" 3 lines. (Remember - one "line"

means 3 rows on the screen.)

We don't need to demonstrate it here, but by using \+Dis-

play+Delete_lines you can delete a group of consecutive lines.

It is not possible to delete a line that has tasks or milestones

on it.

You are now somewhat proficient at adding and editing tasks. Now

proceed to add the following tasks to the project.

o  Task 40, line 2, duration 15, title "Manufacturing" - add

this task after task 25, and before milestone 30.

o  Task 50, line 3, duration 30, title "Programming" - add this

task after task 20, and before milestone 30.

o  Task 60, line 4, duration 33, title "Marketing" - add this

task after task 20, and before milestone 30.

o  Task 70, line 5, duration 20, title "Testing" - add this task

after task 25, and before milestone 30.

The project should appear as in Figure 5.

At this point, save the project so the work doesn't get lost.

To move lines 5 and 6 so that they are after line 2, and ahead

of the present line 3, execute \+Display+Move_lines.

20

When prompted respond as follows;

Move From Line = "5"

Thru Line = "6"

To Line = "3"

The whole command sequence will be repeated for verification.

Type ENTER to proceed, or "n" to abort. The lines should now be

re-ordered as in Figure 6.

21

Figure 5: Tasks Added

MainLine Rev 1.4

.----------------------+---------------------+------------------.

|_____Mar '92__________|___ Apr '92 _________|___ May '92 ______|

|    0    1    2    2  | 0    1    1    2    |    0    1    2   |

|    6    3    0    7  | 3    0    7    4    |    8    5    2   |

Date:16-Mar-92 |MTWTFMTWTFMTWTFMTWTFMT|TFMTWTFMTWTFMTWTFMTWT|MTWTFMTWTFMTWTFMTW|

.--------------+----+----+----+----+----+----+----+----+----+----+----+----+---|

|Blank       1 |Start    .    .    .    .    .    .    .    .    .    .    .   |

|              |*   .    .    .    .    .    .    .    .    .    .    .    .   |

|              | 10 .    .    .    .    .    .    .    .    .    .    .    .   |

|            2 | Define  . Develop .    .    . Manufacturing.    .    .    .   |

|              | =========^===================^--------------^   .    .    .   |

|              |  20.    .  25.    .    .    .  40.    .    .    .    .    .   |

|            3 |    .    . Programming  .    .    .    .    .    .    .    .   |

|              |    .    . -----------------------------^   .    .    .    .   |

|              |    .    .  50.    .    .    .    .    .    .    .    .    .   |

|            4 |    .    . Marketing    .    .    .    .    .    .    .    .   |

|              |    .    . --------------------------------^.    .    .    .   |

|              |    .    .  60.    .    .    .    .    .    .    .    .    .   |

|            5 |    .    .    .    .    .    . Testing .    .    .    .    .   |

|              |    .    .    .    .    .    . ===================^   .    .   |

|              |    .    .    .    .    .    .  70.    .    .    .    .    .   |

|            6 |    .    .    .    .    .    .    .    .    .    .End .    .   |

|              |    .    .    .    .    .    .    .    .    .    .*   .    .   |

|              |    .    .    .    .    .    .    .    .    .    . 30 .    .   |

`--------------+----+----+----+----+----+----+----+----+----+----+----+----+---|

|MTWTFMTWTFMTWTFMTWTFMT|TFMTWTFMTWTFMTWTFMTWT|MTWTFMTWTFMTWTFMTW|

|    0    1    2    2  | 0    1    1    2    |    0    1    2   |

|    6    3    0    7  | 3    0    7    4    |    8    5    2   |

|     Mar '92          |    Apr '92          |    May '92       |

`----------------------+---------------------+------------------'

22

Figure 6: Moved Lines

MainLine Rev 1.4

.----------------------+---------------------+------------------.

|_____Mar '92__________|___ Apr '92 _________|___ May '92 ______|

|    0    1    2    2  | 0    1    1    2    |    0    1    2   |

|    6    3    0    7  | 3    0    7    4    |    8    5    2   |

Date:16-Mar-92 |MTWTFMTWTFMTWTFMTWTFMT|TFMTWTFMTWTFMTWTFMTWT|MTWTFMTWTFMTWTFMTW|

.--------------+----+----+----+----+----+----+----+----+----+----+----+----+---|

|Blank       1 |Start    .    .    .    .    .    .    .    .    .    .    .   |

|              |*   .    .    .    .    .    .    .    .    .    .    .    .   |

|              | 10 .    .    .    .    .    .    .    .    .    .    .    .   |

|            2 | Define  . Develop .    .    . Manufacturing.    .    .    .   |

|              | =========^===================^--------------^   .    .    .   |

|              |  20.    .  25.    .    .    .  40.    .    .    .    .    .   |

|            3 |    .    .    .    .    .    . Testing .    .    .    .    .   |

|              |    .    .    .    .    .    . ===================^   .    .   |

|              |    .    .    .    .    .    .  70.    .    .    .    .    .   |

|            4 |    .    .    .    .    .    .    .    .    .    .End .    .   |

|              |    .    .    .    .    .    .    .    .    .    .*   .    .   |

|              |    .    .    .    .    .    .    .    .    .    . 30 .    .   |

|            5 |    .    . Programming  .    .    .    .    .    .    .    .   |

|              |    .    . -----------------------------^   .    .    .    .   |

|              |    .    .  50.    .    .    .    .    .    .    .    .    .   |

|            6 |    .    . Marketing    .    .    .    .    .    .    .    .   |

|              |    .    . --------------------------------^.    .    .    .   |

|              |    .    .  60.    .    .    .    .    .    .    .    .    .   |

`--------------+----+----+----+----+----+----+----+----+----+----+----+----+---|

|MTWTFMTWTFMTWTFMTWTFMT|TFMTWTFMTWTFMTWTFMTWT|MTWTFMTWTFMTWTFMTW|

|    0    1    2    2  | 0    1    1    2    |    0    1    2   |

|    6    3    0    7  | 3    0    7    4    |    8    5    2   |

|     Mar '92          |    Apr '92          |    May '92       |

`----------------------+---------------------+------------------'

23

4.4  Deleting A Task

Deleting a task is very straightforward.

Execute \+Tasks+Delete, and when prompted enter the ID of the

task or milestone to be deleted.

In some instances it may not be appropriate to delete a task,

and the DELETE will be automatically aborted. This can occur

if deleting the Task would make it impossible to calculate the

Critical Path.

How It Works

The critical path is automatically calculated between a speci-

fied "Start" milestone and a specified "Finish" milestone.

These two milestones are selected by the user. Call up the task

data sheet and you will notice that there is a field called

"Type". Tasks and Milestones are identified here by "t" and "m"

respectively.

The "S" (Start) milestone is fixed for any one project. Any

one milestone may be assigned as the "F" (Finish) Milestone.

The Critical path is calculated between the Start and Finish

milestones.

Requirements

The only requirement is that there be a logical "path" between

the Start and Finish milestones. An interesting result of this

is that you may have other tasks/milestones which originate or

terminate "in space" - no path leading directly from or to the

Start and Finish dates. This is acceptable, and in many cases

reflects real life. (Many other Project Management tools require

that all tasks are connected together and that there are no

"loose ends".)

24

Moving the End Points Around

The "Blank" project starts with exactly one Start and one Finish

Task assigned.

To "move" the Finish designation around, for What-If purposes,

you may temporarily append the Finish characteristic to more

than one milestone, then remove the superfluous one.

Any edits which even temporarily result in having no Finish

milestone will be rejected.

If at any point there is more than one Start or Finish mile-

stone, the critical path calculations may be wrong. This will be

corrected once there are no superfluous Starts and Finishes.

25

4.5  Adding Descriptions to Groups of Tasks

It is helpful to add comments to groups of tasks or milestones.

Comment fields may be added in the left hand field of the dis-

play. There are two comment fields, called Head1 and Head2.

Call up the DEMO project. Edit task #20 ("Define") so that the

Head1 field contains "Project 1" and the Head2 Field contains "-

Hardware". Edit Task 50 ("Programming") so that the Head2 Field

contains "- Software". Finally, edit Task 60 ("Marketing") so

that the Head2 field contains "- Other"

The schedule should now look like Figure 7.

When 2 or more Tasks or milestones on the same line both have

entries in their Head1 or Head2 fields, the Heads from one

task/milestone are arbitrarily selected for display.

4.6  Adding A Date and Labels to The Display

A Date field, and user-defined Labels, are displayed in the

upper left-hand corner of the display. There are 4 Labels, each

15 characters long.

The Date field is assigned or updated whenever the project is

Stored.

The Label fields are set by the user using the commands \+Dis-

play+Labels

A menu will be presented to enter new Labels or to change the

existing ones.

26

Figure 7: Adding Comments

MainLine Rev 1.4

.----------------------+---------------------+------------------.

|_____Mar '92__________|___ Apr '92 _________|___ May '92 ______|

|    0    1    2    2  | 0    1    1    2    |    0    1    2   |

|    6    3    0    7  | 3    0    7    4    |    8    5    2   |

Date:16-Mar-92 |MTWTFMTWTFMTWTFMTWTFMT|TFMTWTFMTWTFMTWTFMTWT|MTWTFMTWTFMTWTFMTW|

.--------------+----+----+----+----+----+----+----+----+----+----+----+----+---|

|Blank       1 |Start    .    .    .    .    .    .    .    .    .    .    .   |

|              |*   .    .    .    .    .    .    .    .    .    .    .    .   |

|              | 10 .    .    .    .    .    .    .    .    .    .    .    .   |

|Project 1   2 | Define  . Develop .    .    . Manufacturing.    .    .    .   |

| - Hardware   | =========^===================^--------------^   .    .    .   |

|              |  20.    .  25.    .    .    .  40.    .    .    .    .    .   |

|            3 |    .    .    .    .    .    . Testing .    .    .    .    .   |

|              |    .    .    .    .    .    . ===================^   .    .   |

|              |    .    .    .    .    .    .  70.    .    .    .    .    .   |

|            4 |    .    .    .    .    .    .    .    .    .    .End .    .   |

|              |    .    .    .    .    .    .    .    .    .    .*   .    .   |

|              |    .    .    .    .    .    .    .    .    .    . 30 .    .   |

|            5 |    .    . Programming  .    .    .    .    .    .    .    .   |

| - Software   |    .    . -----------------------------^   .    .    .    .   |

|              |    .    .  50.    .    .    .    .    .    .    .    .    .   |

|            6 |    .    . Marketing    .    .    .    .    .    .    .    .   |

| - Other      |    .    . --------------------------------^.    .    .    .   |

|              |    .    .  60.    .    .    .    .    .    .    .    .    .   |

`--------------+----+----+----+----+----+----+----+----+----+----+----+----+---|

|MTWTFMTWTFMTWTFMTWTFMT|TFMTWTFMTWTFMTWTFMTWT|MTWTFMTWTFMTWTFMTW|

|    0    1    2    2  | 0    1    1    2    |    0    1    2   |

|    6    3    0    7  | 3    0    7    4    |    8    5    2   |

|     Mar '92          |    Apr '92          |    May '92       |

`----------------------+---------------------+------------------'

27

Figure 8: Date and Label Fields

MainLine Rev 1.4

Label 1        .----------------------+---------------------+------------------.

Label 2        |_____Mar '92__________|___ Apr '92 _________|___ May '92 ______|

Label 3        |    0    1    2    2  | 0    1    1    2    |    0    1    2   |

Label 4        |    6    3    0    7  | 3    0    7    4    |    8    5    2   |

Date:16-Mar-92 |MTWTFMTWTFMTWTFMTWTFMT|TFMTWTFMTWTFMTWTFMTWT|MTWTFMTWTFMTWTFMTW|

.--------------+----+----+----+----+----+----+----+----+----+----+----+----+---|

|Blank       1 |Start    .    .    .    .    .    .    .    .    .    .    .   |

|              |*   .    .    .    .    .    .    .    .    .    .    .    .   |

|              | 10 .    .    .    .    .    .    .    .    .    .    .    .   |

|Project 1   2 | Define  . Develop .    .    . Manufacturing.    .    .    .   |

| - Hardware   | =========^===================^--------------^   .    .    .   |

|              |  20.    .  25.    .    .    .  40.    .    .    .    .    .   |

|            3 |    .    .    .    .    .    . Testing .    .    .    .    .   |

|              |    .    .    .    .    .    . ===================^   .    .   |

|              |    .    .    .    .    .    .  70.    .    .    .    .    .   |

|            4 |    .    .    .    .    .    .    .    .    .    .End .    .   |

|              |    .    .    .    .    .    .    .    .    .    .*   .    .   |

|              |    .    .    .    .    .    .    .    .    .    . 30 .    .   |

|            5 |    .    . Programming  .    .    .    .    .    .    .    .   |

| - Software   |    .    . -----------------------------^   .    .    .    .   |

|              |    .    .  50.    .    .    .    .    .    .    .    .    .   |

|            6 |    .    . Marketing    .    .    .    .    .    .    .    .   |

| - Other      |    .    . --------------------------------^.    .    .    .   |

|              |    .    .  60.    .    .    .    .    .    .    .    .    .   |

`--------------+----+----+----+----+----+----+----+----+----+----+----+----+---|

|MTWTFMTWTFMTWTFMTWTFMT|TFMTWTFMTWTFMTWTFMTWT|MTWTFMTWTFMTWTFMTW|

|    0    1    2    2  | 0    1    1    2    |    0    1    2   |

|    6    3    0    7  | 3    0    7    4    |    8    5    2   |

|     Mar '92          |    Apr '92          |    May '92       |

`----------------------+---------------------+------------------'

28

4.7  Locating Tasks - The "Search" Function

Features are included to make it easy to locate a particular

task. This becomes necessary as a project grows.

You can search through the entire project for one or more

tasks having a particular Title or Descriptive field. Enter

\+Task+Search and you will be prompted to search by Title,

Head1, or Head2. Enter a word or phrase, and all tasks will be

sequentially displayed that match the entry. "Near misses" will

be accepted - i.e. if "Des" is entered, tasks or milestones hav-

ing Titles of "Design", "Destination",and "Oldest" would all be

located. (The search ignores the case of characters). This can

be very helpful when the exact title is not remembered. As each

found task is displayed, the option is presented of stopping

and displaying the screen holding that task, of continuing the

search, or of quitting. If you continue to search and no further

matching tasks are found, you have the option of displaying the

last found match, or of quitting.

It is also possible to locate tasks directly by ID Number (press

CTRL-F when viewing the screen) or by going to the tasks line

if it is known ( press "|" ).

4.8  The Wait Function

It is sometimes useful to specify that a task not actually start

until some fixed time after its predecessors have completed.

This could be accomplished by inserting a "wait" task. However,

MainLine offers the simpler step of assigning a "wait" period

for each task.

In the Demo example, edit the [W]ait field of the task data

sheet for task 40 to have a delay of 10 days. The results are

shown below. The period of waiting is indicated by a string of

"......" characters for tasks off the critical path, or "::::::"

for tasks on the critical path.

29

Figure 9: Using The Task Wait Function

MainLine Rev 1.4

Label 1        .----------------------+---------------------+------------------.

Label 2        |_____Mar '92__________|___ Apr '92 _________|___ May '92 ______|

Label 3        |    0    1    2    2  | 0    1    1    2    |    0    1    2   |

Label 4        |    6    3    0    7  | 3    0    7    4    |    8    5    2   |

Date:16-Mar-92 |MTWTFMTWTFMTWTFMTWTFMT|TFMTWTFMTWTFMTWTFMTWT|MTWTFMTWTFMTWTFMTW|

.--------------+----+----+----+----+----+----+----+----+----+----+----+----+---|

|Blank       1 |Start    .    .    .    .    .    .    .    .    .    .    .   |

|              |*   .    .    .    .    .    .    .    .    .    .    .    .   |

|              | 10 .    .    .    .    .    .    .    .    .    .    .    .   |

|Project 1   2 | Define  . Develop .    .    .    .    . Manufacturing.    .   |

| - Hardware   | =========^===================^::::::::::==============^   .   |

|              |  20.    .  25.    .    .    .    .    .  40.    .    .    .   |

|            3 |    .    .    .    .    .    . Testing .    .    .    .    .   |

|              |    .    .    .    .    .    . -------------------^   .    .   |

|              |    .    .    .    .    .    .  70.    .    .    .    .    .   |

|            4 |    .    .    .    .    .    .    .    .    .    .    .End .   |

|              |    .    .    .    .    .    .    .    .    .    .    .*   .   |

|              |    .    .    .    .    .    .    .    .    .    .    . 30 .   |

|            5 |    .    . Programming  .    .    .    .    .    .    .    .   |

| - Software   |    .    . -----------------------------^   .    .    .    .   |

|              |    .    .  50.    .    .    .    .    .    .    .    .    .   |

|            6 |    .    . Marketing    .    .    .    .    .    .    .    .   |

| - Other      |    .    . --------------------------------^.    .    .    .   |

|              |    .    .  60.    .    .    .    .    .    .    .    .    .   |

`--------------+----+----+----+----+----+----+----+----+----+----+----+----+---|

|MTWTFMTWTFMTWTFMTWTFMT|TFMTWTFMTWTFMTWTFMTWT|MTWTFMTWTFMTWTFMTW|

|    0    1    2    2  | 0    1    1    2    |    0    1    2   |

|    6    3    0    7  | 3    0    7    4    |    8    5    2   |

|     Mar '92          |    Apr '92          |    May '92       |

`----------------------+---------------------+------------------'

30

4.9  Changing Program Configuration

MainLine has several options for changing the appearance of the

screen display or printed output, or for changing fundemental

characteristics of the present project. These are accessed via

the Global command \+Global.

The menu shown in Figure 10 will appear. Information about the

current project will be displayed - the project's name, and

its date of most recent revision. Other information about how

MainLine is currently operating is also displayed. Information

preceeded by a letter in brackets may be changed using this

menu.

To change a setting, enter the bracketted letter in front of

the setting, and then press ENTER. For some settings, a series

of choice-prompts will follow. For others, the setting will

automatically toggle to its only other value.

Example - Changing The Start Date

MainLine uses the current date as the default project start

date. To change it, enter S followed by ENTER. When prompted for

a new start date, enter 6-Jan-92.

Press X followed by ENTER to leave the Global menu. The Calendar

should be appropriately updated. When you store the project

again, the new start date will be stored with it.

The only restriction is that the selected date must be on a

week-day.

Example - Changing The Time Scale

Projects can be displayed using either days or weeks as the ba-

sic unit of time. When the default, days, is used, approximately

4 1\2 months of activity may be displayed on an 80 column screen.

(Wider screen styles, allowing longer time ranges to be dis-

played, are described in the following material.) When a scale

of weeks is used, approx. 7 months activity can be displayed on

an 80 column screen.

31

On the Global menu, enter T and ENTER, and the time scale will

automatically toggle from DAYS to WEEKS.

When a project is stored, the time_scale in use is stored as

part of the project. That time scale will be used when that

project is read back in at a later time.

Note - All Task Durations must always be entered as working-

days, regardless of which time scale is used for displays,

Figure 10: Global Configuration Menu

.------------------------------------------------------------------------------.

!      Project                                Configuration                    !

!      ----------------------------           -----------------------          !

!            Name       : __________                Name  : __________         !

!            Rev Date   : __________            [F] File                       !

!        [S] Start Date : __________            [G] Get                        !

!                                                                              !

!      Screen                                 Printer                          !

!      ----------------------------           ---------------------            !

!        [W] Width      : ___                   [P] Print Width: ___           !

!        [C] Color/Fore : __________            [D] Display ID : ___           !

!                 /Back : __________                                           !

!        [T] Time Scale : __________                                           !

!        [I] ID Display : __________            [X] Exit                       !

!                                                                              !

!             Press Letter in [ ] To Change Function, [x] to Finish            !

!                                                                              !

!   MainLine Rev 1.4   Registered To : ____________________    Ser.No. _____   !

`------------------------------------------------------------------------------'

32

Screen Width and Color

Black and White display, of an 80 column-wide screen, is the

default display mechanism. However, the use of colors, and wider

screen styles is also supported.

Assuming your machine's graphics adapter and monitor support

color, you may change the display colors using the Global Colors

function [C]

A wider time range may be displayed on the screen by changing

the Screen Width to 105 columns using the Global Width function

[W]. The 105 columns mode also provides about 50% more rows of

displayed data. If your system supports VGA graphics, you will

be prompted for a choice of Black/White display ("CGA-style"

graphics) or full color. If your system does not support VGA

graphics, only the Black/White CGA-style is offered.

There are some tradeoffs to using the 105 columns-mode of screen

display;

o  All letters are displayed in Uppercase. (Printed outputs

continue to use Upper and Lower case).

o  Black/White CGA-mode runs somewhat slower than 80-columns

mode. 105-Columns color-mode runs slower still. This is more

noticeable on older, slower machines. On a 20 MHz 386-based

machine, all modes run quite acceptably.

33

Other Settings

Here is a brief description of other settings that may be se-

lected using the Global menu. See Section 6 for more informa-

tion.

o  [I] : Screen ID Display - Controls (yes/no) whether task

identifying numbers are displayed below each task.

This allows mores lines of tasks to be displayed on the screen.

o  [P] : Printer Size - Selects "A" size 80 column output, or

"B" size 132 column output.

o  [D] : Printer ID Display - Similar to Screen ID Display, but

affects printed output only.

Configuration_Files

You can store the configuration so that it will be used auto-

matically the next time MainLine is used. (This saves you from

having to set it up every time). Pressing F and ENTER will file

the present configuration. A default filename will be supplied

(MainLine). Press ENTER to store the configuration as MainLine.

You may find that there are different configurations you prefer

to use on some occasions. You can set a different configuration,

then store it under some other name. It can be recalled at

a later time using the "Get" command (choice G in the Global

Menu). The name of the configuration presently in use is always

displayed in the Global menu.

The configurations are stored in your directory with extension

.cfg. You do not have to specify the extension when storing or

loading a configuration file - that is done automatically.

34

5  Advanced Topics

5.1  System Capabilities

Projects of the following sizes can be handled;

o  Up to 150 Tasks and/or Milestones.

o  Tasks/Milestones may be displayed on up to 1000 "Lines"

o  Dates must fall within the range of 1-Jan-1991 to 1-Jan-2000.

Attempts to exceed these values will usually not be accepted. It

is possible that under some circumstances the program may accept

the value and then crash.

5.2  Following The Critical Path

On larger projects, it may be desirable to trace the tasks and

milestones along the critical path. Pressing the "+" and "-"

keys moves the display forwards or backwards in time along the

critical path.

5.3  The Journal File - Recovering Damaged Project Files

It is possible that at some time the operation will be unwill-

ingly terminated while there are edits that have not been saved.

This may occur due to a system crash (possibly due to a power

outage), or due to some as-yet-unknown bug in the program.

To allow recovery from this, a "backup" or "journal" file of

editing activity is created. Every time you leave the text

editor, the Project File of the current project, including

edits, is copied to the file MLJRNL.PRJ.

To recover, copy the MLJRNL.PRJ to some random project filename

like RECOVER.PRJ. Then start MainLine again, and read in RECOVER

as a project. If it appears to be what you want, exit the pro-

gram and copy RECOVER.PRJ over your original projects' .PRJ

file.

35

5.4  Attaching Fixed Dates to Milestones

A milestone may be entered with no predecessors, with its date

manually entered. This is useful for indicating fixed or exter-

nal occurrences.

To do this, enter a milestone using the normal task addition

procedure. When prompted for "After Task?" enter n for "none".

Enter (or not) a "Before Task?". When the Task Editor Screen

pops up, enter a [B]egin date for the milestone. (Note - for

Tasks, the "none" choice is not appropriate nor is it offered.)

Thereafter, that milestone will appear at that date, regardless

of other tasks or milestones in the project. (You can always

Edit that date.)

Note - Fixed milestones which get on the critical path will

prevent the critical path from reaching all the way back to the

project START milestone. There is nothing wrong with this, but

it may at first appear to be a surprising result.

5.5  Project Rollups

It is often desirable to summarize a group of related tasks

as one larger effort. The Project Rollup task provides this

function.

A Rollup is a special type of task whose beginning and end dates

are linked to a collected group of tasks.

Figure 11 demonstrates this function. Task #100 is a rollup

task. It rolls up the results of tasks 40,70, and 90. Note that

100's start date equals the start date of task 40 (earliest

start of the 40,70,90). Task 100's end date equals the end date

of task 90 (latest end date of 40,70,90) Note that task 70's

start and end lie within the min/max ranges, and so task 70 does

not affect task 100. (Later changes in start/ends of the project

tasks could alter this.)

36

Entering Rollup Tasks - A Rollup task is entered using the same

process as a regular task. Enter it initially as a regular task.

It's predecessors are the tasks it is to rollup. After entering

the rollup task, use the TASK/EDIT function to change its TYPE

to "R" or "r".

Helpful Hint - On a large schedule, Rollups can be used to

provide a concise summary of the overall project. Enter the

whole schedule in the normal fashion. Create a page-worth of

blank lines at the head of the schedule. Place rollups there

which summarize the key subsections of the project.

37

Figure 11: Using Rollup Tasks

MainLine Rev 1.4

.----------------------+---------------------+------------------.

|_____Mar '92__________|___ Apr '92 _________|___ May '92 ______|

|    0    1    2    2  | 0    1    1    2    |    0    1    2   |

|    6    3    0    7  | 3    0    7    4    |    8    5    2   |

Date:16-Mar-92 |MTWTFMTWTFMTWTFMTWTFMT|TFMTWTFMTWTFMTWTFMTWT|MTWTFMTWTFMTWTFMTW|

.--------------+----+----+----+----+----+----+----+----+----+----+----+----+---|

|Blank       1 |Start    .    .    .    .    .    .    .    .    .    .    .   |

|              |*   .    .    .    .    .    .    .    .    .    .    .    .   |

|              | 10 .    .    .    .    .    .    .    .    .    .    .    .   |

|            2 |    . Rollup - 40/70/90 .    .    .    .    .    .    .    .   |

|              |    . -----------------------------^   .    .    .    .    .   |

|              |    .  100    .    .    .    .    .    .    .    .    .    .   |

|            3 | Task Task 40 . Task 50 .    .    .    .    .    .    .    .   |

|              | ====^=========^---------^   .    .    .    .    .    .    .   |

|              |  20.  40.    .  50.    .    .    .    .    .    .    .    .   |

|            4 |    .    .    . Task 90 .    .    .    .    .    .    .    .   |

|              |    .    .    . ===================^   .    .    .    .    .   |

|              |    .    .    .  90.    .    .    .    .    .    .    .    .   |

|            5 | Task 60 . Task 70 .    .    .    . Task 80 .    .    .    .   |

|              | ---------^-------------------^   . =========^   .    .    .   |

|              |  60.    .  70.    .    .    .    .  80.    .    .    .    .   |

|            6 |    .    .    .    .    .    .    .    .    .End .    .    .   |

|              |    .    .    .    .    .    .    .    .    .*   .    .    .   |

|              |    .    .    .    .    .    .    .    .    . 30 .    .    .   |

`--------------+----+----+----+----+----+----+----+----+----+----+----+----+---|

|MTWTFMTWTFMTWTFMTWTFMT|TFMTWTFMTWTFMTWTFMTWT|MTWTFMTWTFMTWTFMTW|

|    0    1    2    2  | 0    1    1    2    |    0    1    2   |

|    6    3    0    7  | 3    0    7    4    |    8    5    2   |

|     Mar '92          |    Apr '92          |    May '92       |

`----------------------+---------------------+------------------'

38

5.6  Renumbering Tasks and Milestones

As a Project is used and modified over time, it may become

desirable to renumber tasks. Work is generally easier if related

tasks have task numbers in the same range.

The Renumber command;

\+Tasks+Renumber

allows this. You may renumber an individual task, a group of

tasks, or all the tasks in the present project. You select

the task(s) to be renumbered, and specify a point to start

renumbering the tasks At. All tasks are renumbered from the

starting point forwards. The tasks will have the same sequence

as in the original range. They will be numbered in steps of 10.

To prevent overlaps, or having multiple tasks with the same

number, a few restrictions are imposed;

o  The new range cannot overlap any tasks which aren't being

renumbered.

o  The new range cannot overlap the "old range" of tasks that

are being renumbered.

Any attempted renumberings which violate the rules are rejected.

The rules may not seem intuitively obvious. If you experiment

with a sample project, though, the principles will soon become

clear.

5.7  Copying A Group of Projects

Very often a sequence of events (a group of tasks and mile-

stones) will need to be entered multiple times in a project.

This is simplified by using the Copy Tasks function. \+Tasks+Copy

will lead to a menu to select a range of tasks for copying.

Since each task must have a unique ID number, the menu will re-

quest a new starting point to re-number the copied tasks to. A

39

sufficient block of blank lines is automatically inserted into

the project following the last task to be copied. The range of

tasks/milestones will then be copied into that area, with the

same relationships, durations, titles and comments. It is advis-

able, but not mandatory, to modify the titles and comments to

make it easier to distinguish the new tasks from the old ones.

40

5.8  Importing Projects

It often becomes desirable to merge together projects which have

been developed separately. This is achieved using the Import

command;

\+Filing+Import

Before any two projects can be merged, it is necessary to make

sure that the two projects do not repeat any task numbers. This

can be done easily using the Renumber function described above.

It is not necessary for you to change the Line Numbers which

are used to display the tasks. The program does this for you.

It re-numbers the "Line Number" entry for each task so that

the imported project starts being displayed after the existing

project. (If you don't like this order, you can always change it

using the Move Lines command.)

The merged projects retain the name of the project that was in

memory when the import started.

If the original and imported projects have different start

dates, the earlier date is selected as the start date for the

merged projects.

There are cases where projects cannot be merged. The reason will

be displayed, along with relevant numbers. The cases are;

o  The imported project cannot have tasks numbers which overlap

the existing project.

o  The total number of tasks in the merged project cannot exceed

the maximum number of tasks allowed per project (150).

o  The total number of lines displayed cannot exceed the maximum

displayed for any one project (1000).

After two projects have been merged, some additional work may be

necessary. For example, if the two projects each have their own

Start and End milestones, it will be necessary to select single

Start and End milestones for the new, merged, project.

41

Also, it will probably be necessary to add links between various

tasks in the two projects - that was possibly the reason for

merging the projects in the first place.

42

6  Command Listing

This section describes briefly all functions that may be ac-

cessed by the menu-command line.

6.1  Filing

The following functions may be accessed by this command;

1. Get - recall an existing project file. You will be prompted

for a project name.

2. Store - Save away the project file which is being worked on.

A default is always given. If you're working on a file which

was read-in, the old name is the default. You may store it

under a new name if you wish.

3. New - Restarts with the "blank" project being displayed.

4. Import - Merge another project file with the project

presently being worked on.

6.2  Global

This allows the setting of certain parameters that affect the

overall operation of the program.

1. Screen Width - 80 or 105 column display

2. Color - Slect forground and background colors

3. Screen ID - Remove the row with that has the task ID numbers.

This results in a more compact display - more lines per

screen or per page of printed report.

4. Calendar Start Date - The Starting point for all dates. This

must be a weekday.

5. Time Scale - Select whether schedule is displayed in units

of days or weeks. Schedule durations are always entered in

working-days.

43

6. Printer Width- Select number of columns displayed per page in

the Schedule report; 80 or 132 (default) columns. All other

reports (.DAT, .RPT) are always 80 columns.

7. Print ID - SImilar to Screen ID, but for printed output.

6.3  Exit

Allows exit from the program.

6.4  Tasks

This is the environment for changing tasks and milestones.

1. Edit - Select an existing Task or Milestone to change its

data.

2. Add Task - Add one or more new tasks.

3. Delete - Delete an existing task or milestone.

4. Find Task - Locate an existing task by its ID number.

5. Renumber - Change the Task Numbers for One, Some, or All

Tasks.

6. Copy - Duplicate a group of tasks and milestones.

6.5  Display

1. Add Lines - Add Blank Lines into the display.

2. Delete Lines - remove unused lines from the display.

3. Move Lines - Move a block of used lines up or down.

4. Labels - Enter or change 4 label-lines on display.

44

6.6  Print

1. Partial Schedule - Print a schedule report covering only

the time-span presently shown on the screen. Output file =

filename.txt

2. All Schedule - Print a schedule report for the period cur-

rently shown on the display through the end of the project.

Adjacent pages of the report will need to be taped together

to obtain a full horizontal view. Output file = filename.txt

3. Date Report - Print a report of the start and end dates for

all tasks and milestones. Output file = filename.dat

4. Task Detail report - List complete information on all tasks

and milestones in the project. Output file = filename.rpt.

45

APPENDIX  A

QUICK-START INFORMATION

A.1  Starting Up

Install MAINLINE by creating a subdirectory on your Hard Disk

such as  C:\MAINLINE and copying MAINLINE.EXE into that

subdirectory. Set the default drive to this directory and

decompress the files by typing MAINLINE followed by CR.

The executable file is ML.EXE. To run the program, at the DOS

prompt type ML followed by ENTER.

A.2  Moving Around The Screen

After a few seconds a screen will be displayed for a blank

project.

The calendar is displayed across the top of the screen.

The duration of all tasks is identified with either "="'s (on

critical path) or with "-"'s (not on critical path.) All mile-

stones have a duration of 0 and are indicated with a "*".

All tasks and milestones have unique identifying TASK ID num-

bers. These are displayed on the schedule below the row of sym-

bols (-,=, or *) indicating the duration of the task/milestone.

The up and down arrow keys may be used to scroll the display up

and down one task-line at a time.

When examining the schedule, the following other controls may be

used;

Quick-Start Information  47

________________________________________________________________

Key___________Function__________________________________________

Down Arrow    Advance Screen One Line

Up Arrow      Back Screen One Line

Right         Move Forwards in time.

Arrow

Left Arrow    Move Backwards in Time

PAGE DOWN     Advance to Next Screen

PAGE UP       Go Back 1 Screen

HOME          Move to Top-most Screen and Start of Calendar

CTRL-T        Move to Top-most Screen

CTRL-B        Move To Bottom-most Screen

CTRL-L        Move Horizontally Left To Start of Calendar

CTRL-R        Move Horizontally Right to Latest Used Date

CTRL-F        Find Task/Milestone

+             Follow the critical path forwards in time

-             Follow the critical path backwards in time

"|"           Go To A Specific Line Number

"\"_or_"/"____Activate_Menu-Command_Line________________________

48  Quick-Start Information

A.3  Calling Up Commands

Pressing "\" or "/" calls up a menu-command line which is dis-

played at the top of the screen. The majority of commands are

activated from this.

One entry on the command line is highlighted. Pressing ENTER

activates the highlighted command. That will either cause a

command to occur or it will cause a "nested" menu to appear.

The highlight may be moved around by either using the horizontal

arrow keys (<- or ->) or by pressing the alphabetic key of the

first letter of the desired command.

Many commands include a verification step ("Do you wish to

do this?). All commands include a confirmation message when

complete.

You may step backwards through the menu-command line (or exit

from the top level) at any time by pressing backspace.

A.4  Basics of Editing and Generating Reports

Existing Tasks and Milestones are edited by activating the

menu-command line and selecting "Tasks" followed by "Edit".

A data sheet will appear listing all current data on the task

or milestone. Individual entries are selected by pressing the

code-letter in front of the data field on the sheet - i.e. "d"

for "duration", "c" for "description, etc. When done, enter "x"

to exit the data-editor with changes, or "q" to quit without

implementing the changes.

New Tasks and Milestones may be added by using the menu-command

to select "Tasks" followed by "add task". You will be prompted

for basic information about the task/milestone, and then the

data sheet will appear.

Similarly, tasks may be deleted using "Tasks" followed by

"Delete". Deletions which make it impossible to calculate the

critical path are not accepted.

Quick-Start Information  49

A.5  Notes on Dates and Calculations

o  Each project must contain one milestone designated as the

"Start" of the Critical Path, and another designated as

the "Finish". These selections are made with the data-sheet

editor by entering "s" and "f" respectively in the "Type"

field for those milestones.

o  There must be a logical path of tasks and milestones between

the Start and Finish milestones. There may be tasks and

milestones which are partially or completely disconnected

("hanging or ending in space"), but there must be a set

of tasks and milestones connecting the Start and Finish

together.

o  Only work-weekdays are used. Weekend-days, if entered, are

rejected.

50  Quick-Start Information

APPENDIX  B

SELECTING OUTPUT FORMATS

A principal function of MainLine is to generate compact schedule

reports suitable for viewing on screens, mailing, hardcopy, or

making viewgraphs for use in presentations.

The schedule is a TEXT file which can be mailed, or printed in

a variety of ways. A schedule printed on 8.5"x11" paper can be

made into a viewgraph or transparency suitable for presenta-

tions. Use the Global command to select whether the output is

80 or 132 columns wide. A schedule that is 132 columns wide can

be printed on 11"x14.5" paper and reduced on a photocopier onto

8.5"x11" paper. Many printers provide a LANDSCAPE option which

allows a schedule 132 columns wide to be printed directly on

8.5"x11" paper.

Selecting Output Formats  51

APPENDIX  C

SERVICE

Registered users are provided service for this program.

Telphone service is provided at (617)489-5639

Additionally, limited service is provided on the COMPUSERVE

network at user ID 70214,210

Service  53