WorkQueue(tm) TUTORIAL

This tutorial consists of this document plus the data files

listed at the end of this section.

It is assumed you have read the PRINTME.DOC document and

installed WorkQueue on your PC.

Each of the three lessons explores progressively more advanced

features and capabilities and builds on the previous lesson.

While exploring a lesson, you are encouraged to experiment -

there are too many features in WorkQueue and too many ways to

achieve results to be taught in a few pages.

Also, learn to use the on-line help. It contains operating

instructions for each screen and the entire user's guide with an

index.

The lessons are built around a single theme - you are the

maintenance manager of a private school and are responsible for

getting a dormitory of rooms painted within the summer break.

The lessons teach you how to deal with both the expected and

unexpected problems that arise while planning the work. It also

shows you how to use WorkQueue to explore alternatives to find

which one best meets the goal.

The only convention you need to be aware of while taking the

lessons is every place you need to enter keystrokes is marked

with a >> .

The following are files necessary to take this tutorial:

LESSON1.RDC, LESSON1.PDC, LESSON1.WQP, LESSON2.RDC,

LESSON2.PDC, LESSON2.WQP, LESSON3.RDC, LESSON3.PDC,

LESSON3.WQP, HOLIDAY.HDC

You will be allowed to change and save these files so keep a copy

of the originals for others to use with this tutorial.

1. LESSON ONE

This section of the tutorial covers the basic aspects of

WorkQueue including:

Starting and stopping the system.

Copyright 1989-1992 by Lane Davis                          Page 1

How to use the action bar, menus, dialogue boxes and list

boxes.

How use the work plan, staff plan and holiday schedule to

calculate a work schedule.

Start WorkQueue by changing to the directory you keep the system

files in and entering:

>> WQ

1.1  Choosing a Project

The first thing you'll see is the opening screen that discusses

Shareware and gives an overview of licensing terms. If this copy

of WorkQueue is licensed, you won't see this information.

You proceed past this screen by pressing any key.

Next is displayed is a "dialogue box" asking for the name of the

project you want to work on. Dialogue boxes are used throughout

WorkQueue to get information about what you want to do next.

>> Press F4 to display a list box of projects.

WorkQueue uses list boxes for many functions and they all work

the same:

Use the PgDn or PgUp keys to scroll through the list.

Press any alphabetic key to automatically scroll the list to

the first item that starts with that letter. Press the

letter again to move the bar to the next item that starts

with that letter, etc.

Use the up and down arrow keys to move the bar to your

selection and press Enter.

>> Choose the "LESSON1" project.

The three data files will then be automatically filled in along

with a description of the project:

Work Plan                LESSON1.RDC

Staff Plan               LESSON1.PDC

Holiday Schedule         HOLIDAY.HDC

>> Press the Enter key to continue.

Copyright 1989-1992 by Lane Davis                          Page 2

The "action bar" will appear across the top of the screen. This

lists each of the actions you can take. Choosing an action will

usually display a "drop-down" menu from which you choose an item,

others will switch to a dialogue box to complete the action.

You can make choices from either the action bar or a drop-down

menu by:

Moving the selection bar to your choice and pressing enter

(use the arrow keys to move the bar).

Each choice has a capital letter in it, you can activate

that choice by pressing that letter on the keyboard (either

upper or lower case).

1.2  The Work Plan

>> Press "v" to show the "view" menu.

>> Press "w" to show the work plan.

This work plan consists of only one job - to paint a dormitory

full of rooms.

>> Press F1 to review the operating instructions for Jobs and

while you are in the help screen, also review the User's Guide

for the Work Plan. When the help screen appears, notice there is

a short "horizontal" menu with a choice bar at the bottom. You

can select a category of help by using the left and right arrow

keys to move the bar to a category and press enter to display it.

The exception is the Index - you can only display it by pressing

the F4 key. This is an index to the user's guide by subject and

table of contents. When you are looking at a WorkQueue screen and

press F1, the help screen shown next is for that screen. In other

words, help is context sensitive. The index is provided when you

need to review a subject "out of context".

>> Press Escape to exit help.

Note that the Job has a Target Date of 8/6. The school's Business

Manager (your boss) has told you the new Freshmen will begin

moving into the dormitory on that date. In other words, all

painting must be finished by then.

>> Place the cursor anywhere on the job and press Enter to show

the Tasks for that Job.

There are 18 tasks, one for each room.

Copyright 1989-1992 by Lane Davis                          Page 3

Notice that only the Job Number, Task Number, Task descriptions,

Skill and Remaining Workdays (REM W/D) are filled in. These are

generally the only data elements needed to create a task where

the work can proceed at whatever pace the staff can support. This

type of work is called "staff driven" - for a description of the

other work types that can be used, look at the User's Guide.

>> Press F1 to review the operating instructions for Tasks and

while you are in the on-line help, review the User's Guide and

Glossary.

1.3  The Staff Plan

>> Press Esc(ape) to return to the Job Screen.

>> Press Esc again to "pop-up" the menus.

>> Press "v" to "pull down" the View menu.

>> Press "t" to view the Staff Plan.

There is only one person available to paint the rooms and he has

one skill - "PAI" for "PAINTING". The skill could have been named

any 1-3 letters as long as it meant "painting".

>> Place the cursor anywhere on the person and press Enter to

show the Time Records. There is only one time record for this

person:

A "base rate" that says that person is available 5 days per

week.

>> Press F1 to review the operating instructions and user's guide

for Time Records.

1.4  The Holiday Schedule

>> Press Esc to return to the Person Screen and Esc again to show

the menus.

>> Press "v" to display the view menu and "d" to display the

Holiday Schedule.

>> Press F1 to review the operating instructions and user's

guide.

Copyright 1989-1992 by Lane Davis                          Page 4

1.5  The Work Schedule

>> Press Esc to activate the menus, "s" to display the schedule

menu and "c" to compute a schedule.

The next thing you'll see is the Work Scheduling dialogue box.

From here you can choose the duration of the schedule to be

computed and the date to start from.

>> Press F1 to review the operating instructions.

>> Key in "7/1/91" for the start date and "1" for the duration,

then press Enter to proceed (this lesson was designed to use this

date and duration - you could have used any other).

The next screen is the Work Schedule (job level) - it shows the

duration of each job - only one in this case.

>> Press F1 to review the operating instructions and user's

guide.

Note the following:

Work started the week of 7/1 and finished the week of 8/8.

In the first week (7/1) only three days of work were

scheduled because the Independence Day holiday is both the

4th and 5th.

In the last week, 0.4 days of work were scheduled because

that was all the work need to finish the job.

In the 4 weeks between, 5 days of work were scheduled each

week.

The target date shows on the schedule as a "t".

This adds up 23.4 work days. The total number of workdays

scheduled will always be the number of workdays in the work plan

unless there is work that couldn't be scheduled.

>> Place the cursor on the job and press Enter.

This will show the schedule for the Tasks contained in the job.

>> Press F1 to review the operating instructions and user's

guide.

Copyright 1989-1992 by Lane Davis                          Page 5

2. LESSON TWO

>> Return to the main menu (by pressing Esc until the menus

appear).

>> Press "f" and then "c" to change to another project (lesson).

Choose the project named "LESSON2".

2.1  Not-Before Date

You have just been told that room number 11 will not be vacated

until 7/10.

To see how this affects the schedule, view the work plan and

bring the task for painting room number 11 up on the screen.

Add a Not-Before date of 7/10/91.

Compute a new schedule with the same start date and duration as

before. Note that the work will still be done by 8/5 so you can

still finish the work on time. It simply means that room number

11 won't be done first.

2.2  Vacation

Jerry (you're only painter) just told you his son is getting

married on 7/17 and he needs 5 days vacation starting 7/15 to

attend the wedding.

View the Staff Plan and bring Jerry's Time Records up on the

screen.

You need to add a new time record to describe Jerry's vacation.

Read the operating instructions (F1) to find out how.

The new Time Record should contain:

Start Date:    7/15/91

Stop Date:     7/19/91

Work Rate:     0.0

Description:   Vacation

Re-compute the schedule. Bad news - you can't make the target

date based on the current staff and work plans (work is not

completed until 8/9). Also, note that there were 1.3 days of work

(room number 36) that couldn't be completed.

Copyright 1989-1992 by Lane Davis                          Page 6

The reason for the incomplete work is Jerry is available to paint

only until 8/9 - he must begin painting the Headmaster's house

after that, a job that cannot be postponed.

2.3  Overtime

Since changing the target date would be very difficult, if not

impossible, there are only three options:

Tell Jerry he can't attend his son's wedding.

Pay Jerry to work enough overtime to finish on schedule.

Hire an additional painter.

You don't consider the first option reasonable and, considering

that hiring a new painter might take awhile, you decide to use

overtime to make the target date.

The question is - how much overtime? Does it need to be before

the wedding or can it wait until after?

To answer these questions, Add another time record for Jerry (in

the staff plan) and give it the following data:

Start Date:    7/22/91

Stop Date:     8/5/91

Work Rate:     2.0

Description:   Overtime

This starts the overtime after the wedding. When you re-compute

the schedule, it yields a completion date of 8/6 - barely in

time. This also means if anything else goes wrong, the target

date is once again in jeopardy but you decide to go with this

plan anyway.

3. LESSON THREE

Load the project named "LESSON3"

You have just found out that a plumbing leak occurred on the

third floor of the dormitory in room 36 and repairs will be

needed on the second floor, to room 26, since the water leaked

down through the walls and ruined the plaster (this is an old

dormitory).

Copyright 1989-1992 by Lane Davis                          Page 7

3.1  Networking

To accurately represent this delay, you will have to add a task

for the repairs in room 26 and "network" it with the task to

paint room 26. In networking jargon, this means making the

painting task "dependent" on the repair task.

First, add a task for the room repairs. The most logical place to

put the task is just before the painting task. Display the tasks

on the screen and move the cursor to the task for painting room

number 26.

>> Press Alt+I (a lower-case "i" is ok) to insert a new task just

before the task for room number 26.

The new task will be empty except for the Job and Task Numbers.

To complete the task, key in the following information:

Description:             Repairs to 26

Remaining Workdays:      3.0

To Node:                 REP1

(In order to key in the To Node, you will first need to scroll

laterally by pressing the F9 key.)

When you key anything into a Node (either From or To), that node

is automatically created and can be referred to by any number of

other tasks as a From or To node. The node name, in this case

"REP1", can be any 1-4 characters you choose.

To complete the networking, key the same node name (REP1) into

the From Node of the painting Task.

Recompute the schedule.

PROBLEM: The Job Schedule screen shows unfinished work. To find

out why, display the Task Schedule screen and then press F1 to

interpret the problem codes on the right side of the screen.

It turns out there are two problems:

A.   The repair task couldn't be started because there is no

one with plumbing skills in the staff plan.

B.   Since the repair task wasn't finished, the painting

task for room 26 couldn't be started because you

"networked" the two (you made starting the paining task

dependent on the completion of the repairs).

Copyright 1989-1992 by Lane Davis                          Page 8

To fix this, add a plumber to the staff plan:

Initials:      MP

Name:          Mister Plumber

Skill1:        PLU

Don't forget to add a time record:

Start Date:    8/2/91

Stop Date:     8/7/91

Work Rate:     5.0

Description:   (leave blank - not needed).

Now re-compute the schedule.

Now all the work is being completed but you're 2 days behind

schedule. In this case, you are unable to get another plumber any

earlier so you choose to write a letter to the two students

scheduled to move into room 26 to tell them not to arrive until

August 9th.

4. FURTHER "STUDY"

The remaining WorkQueue facilities can be explored by

experimentation and reading the on-line help. At a minimum,

review the following:

The "List" facility. On most screens there are data entry

areas where, if you press F4, a list of alternatives is

shown from which you can choose. For example, try it on a

date element such as the Target Date in the Work Plan.

Staff Utilization Staff Availability Analysis. These are

menu items that help you improve the utilization of you

staff and also help diagnose scheduling problems.

Filtering - a menu item under "Options". Filters let you

limit what you see on the screen or print in a report. This

can be very useful, especially on a complex schedule. For

example, you can display the work schedule for only one

person.

Reports - the best way to see what reports are available is

to print them for one of the lessons.

Copyright 1989-1992 by Lane Davis                          Page 9